## Work Order Tracking Form
Work Order Tracker
Work Order # | Description | Reported By | Repairs Made | Report Date | Completion Date | % complete | Status | Reason Active
#001 | Standing water issues on the Corner of Haven Blv and Laurel Oak | HOA | Installed french drain fromm street draining back to the ditch | 2017-08-01 | 2017-08-15 | 100% | Complete
#002 | Brick column under pavillion broken and missing bricks | Safety committee (Lawrence) | Replaced broken bricks (Safety Committee) | 2017-12-01 | 2017-12-05 | 100% | Complete
#003 | Rut on West sided of Laurel Oak and Haven Blv | Millard Perkins Lot85 | Rut filled in with crushed concrete (Safety Committee) | 2017-12-04 | 2018-01-15 | 100% | Complete
#004 | Curb broken at all four corners on the first island going out of the subdivision | Safety committee (Lawrence) | West end corners have been repaired (Safety Committee) | 2017-12-13 |  | 50% | Active | East end corners have not been repaired need to drfill into curb and install re-bar
#005 | Install park rules and parking signs | HOA | Park rules and parking lot signs installed | 2017-11-30 | 2017-12-21 | 100% | Complete
#006 | Extend fence around pond | HOA |  | 2017-12-01 |  | 0% | Active | On hold
#007 | Install lighting in park | HOA | Lighting installed by Entergery on 3/5/18 | 2017-12-01 |  | 100% | Complete
#008 | Install electrical outlets at pavilions at the park | HOA |  | 2017-12-01 |  | 0% | Active | On hold
#009 | Power wash concert walkways in the park | Safety committee (Lawrence) | Power wash the walkways | 2017-12-23 |  | 25% | Active | Need to continue power wash
#010 | Wrap water lines in park due to freezing weather | HOA | Wrapped water lines with foam insullation | 2017-12-31 | 2017-12-31 | 100% | Complete
#11 | Apply mulch around playground equipment | HOA | Mulch applied around swing set | 2018-01-06 | 2018-04-28 | 100% | Complete
| Walking trail / walking surface in poor condition | Safety committee (Lawrence) |  | 2018-01-31 | 2019-01-15 | 100% | Complete
| Drainage in park poor | Safety committee (Lawrence) |  | 2018-01-31 |  | 0% | Active | On hold
| Electric trench needs filled | Safety committee (Lawrence) | Trench filled in by safety committee | 2018-01-31 | 2018-02-10 | 100% | Complete
| Dead tree along ditch by pond needs taken down | Safety committee (Lawrence) |  | 2018-01-31 |  | 0% | Active | On hold
| Install rock at culvert by pond to prevent erosion | HOA | Rocks installed | 2018-03-01 | 2018-03-22 | 100% | Complete
| Install french drain on Haven blvd. and Laurel Oak due to water standing in street | HOA | Installed french drain fromm street draining back to the ditch | 2018-02-15 | 2018-03-20 | 100% | Complete
| Overhaul land scaping at park sign | HOA | Removed old landscaping and added new schrubs, mulch and sprinkler system | 3/185/18 | 2018-04-04 | 100% | Complete
| Install street light at the end of Spanish Oak | HOA | Street light installed by Entergery | 2018-03-05 | 2018-04-03 | 100% | Complete
| Install additional swing bays and swings in park | HOA |  | 2018-01-01 | 2018-05-12 | 100% | Complete
| Install french drain south side across from first island going out of the subdivision for sprinkler run off | Lot #1 | French drain installed | 2018-04-01 | 2018-04-21 | 100%
| Trim shurbs at front enterance | Homeowner | shurbs trimmed | 2018-05-01 | 2018-05-24 | 100% | 1
| Clumps of mud on pad under big pavilion | Homeowner | Board cleaned up the mud clumps | 5/19/2018 | 2018-05-26 | 100% | Complete
| Weeds in flower bed at front enterance sign | The Board | Board removed weeds from flower bed | 2018-06-01 | 2018-06-10 | 100% | 1
| Weeds around flag pole base | The Board | Board removed weeds from around flag pole base | 2018-06-12 | 2018-06-15 | 100% | 1
| Plant cypress trees around edge of pond | The Board | Cypress tress planted around edge of pond by the Board | 2018-06-08 | 2018-06-14 | 100% | 1
| Graffiti on big pavilion floor | Homeowner | Board pressured washed entire floor and removed graffiti | 2018-07-06 | 2018-07-06 | 100% | 1
| Fire ant mounds in park | Homeowner | Board applied fire ant killer to ant mounds | 2018-07-21 | 2018-07-22 | 100% | 1
| Bolders at front entrance out of place | The Board | Bolders put back in place | 2018-05-10 | 2018-08-08 | 100% | 1
| Water leak at sprinkler valve box | Homeowner | Replaced section of pipe and control valve | 2018-08-01 | 2018-09-07 | 100% | 1
| Drainage culverts at North side driveway to parking at park blocked on both sides of driveway | Safety committee (Lawrence) | Cleaned out front of culvert and repositioned rocks around culvert | 2018-09-25 | 2018-09-25 | 100% | 1
| Plant cypress , crepe myrtle and magonila trees around pond | The Board | Trees planted around pond by Lawrence, Cheri, Abbey and Vernon | 2018-09-30 | 2018-09-30 | 100% | 1
| Fire ant mounds in park | Homeowner | Board sprayed ant mounds | 2018-10-28 | 2018-10-29 | 100% | 1
| Center support post on soccer goal keeps falling out | The Board | Installed screws to secure center support post | 2018-11-15 | 2018-11-15 | 100% | 1
| Soccer goals broken at top cross bar and ball rack broken | The Board | Rfemoved soccer goals | 2018-12-18 |  |  | Active | On hold
| Walking trail needs heavy maintenance | The Board | Installed crushed lime stone | 2019-01-01 | 2019-01-15 | 100% | 1
| Install pad in park for basketball goal | HOA |  | 2019-01-31 | 2019-05-02 | 100% | Complete
| Install new sign on first island going out of the subdivision | The Board | New sign installed | 2019-04-01 | 2019-05-06 | 100% | 1
| Install new concrete tables and benches at park | The Board |  | 2019-05-01 |  | 0% |  | Tables and benches on order
Formulas:
Status = IFERROR(IF(WorkOrders[[#This Row],[% complete]]=1,1,IF(ISBLANK(WorkOrders[[#This Row],[Completion Date]]),"",IF(AND(TODAY()>WorkOrders[[#This Row],[Completion Date]],WorkOrders[[#This Row],[% complete]]<>1),0,-1))), "")