## To-do list
2023 / 2024 | Maintenance / Projects Tracker
Task | Priority | Status | Start date | Date Completed | % Complete | Column1 | Done/Overdue? | Notes
Extend fence by bpond area | Low | In Progress | 2023-10-15 |  | 75% |  | Overdue | Fence is installed, the gated needs to be installed
Install lighting at the parvillions at the park | High | In Progress | 2023-10-25 |  | 50% |  | Overdue | Conduit and wiring installed at the big pavillion need to install light fixtures. Ned to install conduit, wiring and lightn fixtures at the small parvillion
Install covered structure on slab next to basketball goal | Normal | Not Started | 1905-07-16 |  | 0% |  | Overdue | Need to buy materials
Move lights from behind front entrance wall to the front of the wall | Normal | Not Started |  |  | 0% |  | Overdue | Need to coordnate with the electrician, reported from safety committee
Replace dead trees and shrubs inn the front of subdivision | Normal | Not Started |  |  | 0% |  | Overdue | We will start this project in the spring of 2024, reported from safety committee
Trim low hanging branches on trees in the park | Normal | In Progress | 2023-11-30 |  | 0% |  | Overdue | Need to coordnate with landscape people, reported from safety committee
Need to rake or grade parking lot at the park | Normal | Not Started | 2023-12-10 |  | 0% |  | Overdue | Need to contact one ofm the homeowners for help that took care of this in the past, reported from safety committee
On / Off timer for sprinklers at the front of subdivision needs to be reprogramed and some sprinkler head to be adjusted | Normal | Complete | 2023-01-05 |  | 100% |  | Done | Taken care of by two homeowners
Relocate tree that was cut down back by the pond | Low | Not Started | 2024-01-15 |  | 0% |  | Overdue
-1
-1
-1